## Slide 1: Automated Object Retrieval System Kick Off Meeting
25th January 2017

## Slide 2: Agenda
Project Overview
Objectives & Scope
Estimation
Stakeholders
Roles and Responsibilities
Project Life Cycle
Infrastructure Need
Issues
Communication Plan
Key Success Factors

## Slide 3: Project Overview
Working of the Project

## Slide 4: Objective and Scope
Objective
  We will be developing a full proof object retrieval system.
Scope
  Vehicle and forklift.
  Database management using SQLite or SQLite3.
  Firmware of Vehicle and Forklift Python 2.7.6 or 3.X .
  GUI using EasyGui.
  All possible security measures.

## Slide 5: Estimation
Project Type | Milestone based
Estimated Duration (in PDs/Hrs.) | 1952 Hrs.
Planned Start Date (DD-MMM-YYYY) | 25th January 2018
Planned End Date (DD-MMM-YYYY) | 15th March 2019
Actual Start Date (DD-MMM-YYYY) | 25th January 2018
Notes: Estimation Technique:
Function point estimation/Complexity / Lines of Code (it is recommended to mention the name of the template that is used for estimation)
Engagement Type:
Onsite
Offshore
On site & Offshore
Billing Type:
Time and Material
Time and Material with Cap
Fixed Price

## Slide 6: Stakeholders
Project Team Details | 
Project Manager | Kaushal Vala
Project Leader(s) | Devaj Parikh
Team Members | Devanshi Patoliya, Durva Shah, Parita Shukla, Sadhika Sajeev.
Support Function Details | 
QEG | Kaushal Vala, Devaj Parikh
Admin Support | C.S.P.I.T Admin
Purchase Support | GUJCOST
Point of Contacts | 
Delivery Manager | Dr. Trushit Upadhyaya
Account Manager | Dr. A.D. Patel

## Slide 7: Roles and Responsibilities
Role | Responsibilities | Accountable Person
Account Manager | Tracking and monitoring billing milestones | Dr. A.D. Patel
Delivery Manager | Monitoring progress of overall project, Milestones, part of steercom Meetings | Dr. Trushit Upadhyaya
Project Manager | Project Planning & Monitoring, Estimation & Scheduling, Resource, Management, Status Reporting, Change Management | Devaj Parikh
Project Leader/ Technical Leader | Technical Planning & Monitoring, On Time Deliverable Assurance | Devaj Parikh
Configuration Manager | Configuration Control, Release Management, Change Management, Reporting Configuration Status Accounting | Devaj Parikh
Quality Excellence | Project Process Facilitation, Reviews of documents (From Process Perspective), Configuration Audits | Kaushal Vala
Engineers/Developers | Works on the Development of the Project/Product | All team members
Testing Team Members | Validation/Testing, Test | All team members
Delivery Sign Off Authority | Sign off the Deliverables | Kaushal Vala

## Slide 8: Project Life Cycle
Project Execution Model
  Waterfall lifecycle model will be followed for the project
Processes to be followed
  Project Initiation
  Proposal / SoW Review
  Project initiation note
  Kickoff
  Project Planning
  Training plan
  Configuration management
  Risk management process
  Project Execution / Project Monitoring and Control
  Change management
  Decision analysis and resolution
  Quality Assurance
  Project Closure

## Slide 9: Infrastructure Needed
Software Requirements
  Python
  EasyGUI
  SQLite3
  Eclipse; PythonIDE
  Microsoft – project plan, power point, spreadsheet and word doc
  SVN / GIT/ GoogleDrive
Hardware Requirements
  Raspberry Pi
  Gerber viewer

## Slide 10: Issues
N/A

## Slide 11: Communication Plan
Type of Meetings | Periodicity | Team Members | QEG Member | Support Group | Project Manager/ Leader | Delivery Manager | Sales | Centre/ Division Head
Project Status meeting with customer | Weekly | Y | Y | N | Y | N | N | N
Project Status meeting with internal | Weekly | Y | N | N | Y | N | N | N
Sr. Management meeting | Monthly | N | Y | N | Y | N | N | N
Milestone Review Meetings | Based on milestone completion | N | Y | N | Y | Y | N | Y

## Slide 12: Key Success Factors
A scalable framework which can
  Store and manage Data of Objects
  Fetch or place the object to their designated places.
  Generate Reports