## Schedule
# | Task Details | Status | Start Date | Due date | New Due Date | Actual Start Date | Actual End Date | Target Version | Description
1 | Car Simulator Software/Firmware | In Progress | 2017-11-01 | 2017-12-26 | 2018-01-06 | 2017-11-01 |  | Milestone 1
2 | Car Simulator Assembled Boards Available at eI | Closed | 2017-11-01 | 2017-12-21 |  | 2017-11-01 | 2017-12-21 | Milestone 1
3 | Car Simulator HW bring-up & functional testing | In Progress | 2017-12-22 | 2018-01-22 | 2018-02-15 | 2017-12-22 |  | Milestone 1 | 1/8: The H/W related items which are open/on hold due to dependency on Sesha will be further delayed.
4 | OCPP 1.6 Server library & Interface | Closed | 2017-11-13 | 2017-12-22 | 2018-01-10 | 2017-11-14 | 2018-01-09 | Milestone 1
5 | Test Automation Framework | In Progress | 2017-11-01 | 2017-12-29 | 2018-01-15 | 2017-11-13 |  | Milestone 1
6 | Cloud/Web Pages Automation | In Progress | 2017-11-01 | 2017-12-29 | 2018-01-15 | 2017-11-06 |  | Milestone 1
7 | Test framework | In Progress | 2017-11-01 | 2017-12-29 | 2018-01-15 | 2017-11-07 |  | Milestone 1
8 | Jenkins automation | Closed | 2017-11-01 | 2017-12-29 | 2018-01-15 | 2017-11-13 | 2018-01-04 | Milestone 1
9 | Communication Modules | In Progress | 2017-11-20 | 2017-12-29 | 2018-01-10 | 2017-12-05 |  | Milestone 1 | Stand alone application in progress
10 | Megger programming & automation | Closed | 2017-11-15 | 2017-12-01 |  | 2017-11-15 | 2017-11-29 | Milestone 1 | Stand alone application implemented
11 | IP Network power switch & automation | Closed | 2017-11-15 | 2017-11-22 |  | 2017-11-15 | 2017-11-21 | Milestone 1 | Stand alone application implemented
12 | Documentation | In Progress | 2017-11-30 | 2017-12-31 |  |  |  | Milestone 1
13 | Test Plan | In Progress | 2017-11-15 | 2017-12-15 | 2018-01-28 | 2017-11-25 |  | Milestone 1
14 | EVSE Features Testing | In Progress | 2017-11-01 | 2017-12-29 | 2018-01-20 | 2017-11-01 |  | Milestone 1
15 | EVSE Features Test Cases (10%) | Closed | 2017-11-01 | 2017-12-29 |  | 2017-11-01 | 2017-11-21 | Milestone 1 | Test cases and scenarios discussion with Siemens Team 9 Test cases completed (and reviewed by Siemens)
16 | EVSE Features Test Procedures (10%) | In Progress | 2017-12-01 | 2017-12-29 | 2018-01-20 | 2017-12-04 |  | Milestone 1
17 | OCPP Client Testing | In Progress | 2017-12-01 | 2017-12-29 |  |  |  | Milestone 1
18 | OCPP Test Cases (30%) | In Progress | 2017-12-01 | 2017-12-29 |  | 2017-11-05 | 2017-11-30 | Milestone 1 | OCPP 1.6 test cases completed. Siemens to review and signoff
19 | OCPP Test Procedures (30%) | New | 2017-12-01 | 2017-12-29 | 2018-01-15 |  |  | Milestone 1
20 | EVSE Feature Testing | New | 2018-01-01 | 2018-01-31 | 2018-02-21 |  |  | Milestone 2
21 | EVSE Features Test Cases | In Progress | 2018-01-01 | 2018-01-31 | 2018-02-21 | 2017-11-01 | 2017-12-31 | Milestone 2 | Test cases and scenarios discussion with Siemens Team
22 | EVSE Features Test Procedures | New | 2018-01-01 | 2018-01-31 | 2018-02-21 |  |  | Milestone 2
23 | OCPP Client Testing | New | 2018-01-01 | 2018-01-31 | 2018-02-21 |  |  | Milestone 2
24 | OCPP Test Cases (100%) | In Progress | 2018-01-01 | 2018-01-31 |  | 2017-11-05 | 2017-11-30 | Milestone 2 | OCPP 1.6 test cases completed. Siemens to review and signoff
25 | OCPP Test Procedures (100%) | New | 2018-01-01 | 2018-01-31 | 2018-02-21 |  |  | Milestone 2
26 | EVSE Feature Testing | In Progress | 2018-02-01 | 2018-02-28 | 2018-03-21 |  |  | Milestone 3
27 | EVSE Features Test Cases | In Progress | 2018-02-01 | 2018-02-28 | 2018-03-10 | 2017-11-01 | 2017-12-31 | Milestone 3 | test cases completed. Siemens to review and signoff
28 | EVSE Features Test Procedures | New | 2018-02-01 | 2018-02-28 | 2018-03-21 |  |  | Milestone 3
29 | EVSE Feature Testing | New | 2018-03-01 | 2018-04-15 | 2018-05-06 |  |  | Milestone 4
30 | EVSE Features Test Cases | In Progress | 2018-03-01 | 2018-04-15 | 2018-04-25 | 2017-11-01 | 2017-12-31 | Milestone 4 | test cases completed. Siemens to review and signoff
31 | EVSE Features Test Procedures | New | 2018-03-01 | 2018-04-15 | 2018-05-06 |  |  | Milestone 4
Formulas:
New Due Date = ([Due date]+21)

## SoW Milestones
# | Project Phase / Milestone | Deliverables from eInfochips | Release to Siemens | Required from Siemens/
|  |  | (in weeks) | Dependencies on Siemens
M0 | Kick-off | - | T0 | PO
M1 | Test Automation Framework | Documentation/manual for automation framework | T0 + 8
| Car Simulator hardware + firmware | Code for Car Simulator firmware.
Layout board file & Gerber data. 10 fabricated boards
| OCPP 1.6 Server | OCPP 1.6 Server
| Testing of OCPP Client (30%) | OCPP Client test cases, procedures and report
| Testing of EVSE features (10%) | EVSE features test cases, procedures and report
Test report review & feedback
M2 |  |  | T0 + 12 | Test report review & feedback
| Testing of OCPP Client (100%) | OCPP Client test cases, procedures and report
| Testing of EVSE features (30%) | EVSE features test cases, procedures and report
M3 | Testing of EVSE features (60%) | EVSE features test cases, procedures and report | T0 + 16 | Test report review & feedback
M4 | Testing of EVSE features (100%) | EVSE features test cases, procedures and report | T0 + 22 | Test report review & feedback