## Slide 1: Siemens EVSE Automation Weekly Project Status Updates
Date: 23rd November 2017
eInfochips Confidential
Product Design Services & Solutions
Product Engineering| Semiconductor

## Slide 2: Agenda
  Work status this week: 17th November to 22nd November
  Plan for next week: 23rd November to 29th November
  Key Decisions
  Dependencies and help needed
  Miscellaneous Information/Updates

## Slide 3: Work Status for this week
Test Automation Framework
  Completed Test Environment setup for Cloud Web App Automation - Done
  Preliminary implementation for basics Automation framework for Cloud Web app - (In Progress)
  Completed installation of Jenkins, Pylint and Maven for packaging and build - Done
  OCPP server interface development
    Client interface simulator for proof of concept - Done
  Configuration & Automation of IP power switch – Standalone implementation done
  Configuration & Automation of Megger SMRT1 - Standalone implementation done
  Test Plan – In Progress
Hardware
  Placement review completed
  Completed routing of the new parts added & reviewed
  Footprint correction completed
  Review of isolation criteria completed
EVSE Testing
  Completed test cases for 5 new OCPP functionalities (listed on slide # 5)
  Implemented changes as per review feedback from Paul

## Slide 4: Work Status – EVSE Features Test Cases (No Change)
# | Features | Test Cases Status
1 | System Configuration | Done
2 | SAE J1772 State levels | Done
3 | CCID Time Response (I vs. non-I) | Not started
4 | CCID Auto Reset (15min.) | In Progress
5 | Max Current Switch Settings | Done
6 | Pause Button (Local & Web App) | In Progress
7 | 2/4/6/8 Hr. Delay Button | Not started
8 | Cold Start with Random Delay | In Progress
9 | Over/ Under Voltage detection | Done
10 | Function Memory after Power Cycle (Pause, Delay, Remote, Lock) | In Progress
11 | Local Lock with Lock Enabled | In Progress
12 | Local Lock with Lock Disabled | In Progress
13 | Serial Communications (RS-485) | Done
14 | Fault test & Non Volatile Memory (Fault Log) | In Progress
15 | Non Volatile Memory (Energy Measurements) | Done
16 | RTC | Done
17 | Remote Control Via Web App | No separate test for this
18 | OTA updateable (CC2538) | Not started
19 | Remote Control via OCPP App | Refer separate table for OCPP
20 | EVSE Commissioning | Done
21 | Power Level adjustment (Verify pilot duty cycle) | Done
22 | Local Override of Cloud Remote | In Progress
23 | Firmware version verification on the Web App | In Progress

## Slide 5: Work Status – OCPP Features Test Cases
# | Feature | Test Cases Status
1 | BootNotification | Done
2 | Heartbeat | Done
3 | MeterValues | In Progress
4 | StartTransaction | Done
5 | StatusNotification | Done
6 | StopTransaction | Done
7 | ChangeConfiguration | In Progress
8 | ClearChargingProfile | In Progress
9 | GetConfiguration | Done
10 | RemoteStartTransaction | Done
11 | RemoteStopTransaction | Done
12 | SetChargingProfileRequest | In Progress
13 | TriggerMessageRequest | Done

## Slide 6: Work plan for next week
Test Automation Framework
  Automation framework design and architecture.
  Building Python project using Maven to create POM file and configure it in framework.
  Verification of Socket connection and communication with OCPP Server.
  Preparing request response classes according to JSON format that are being sent and received by EVSE and server
  Test Plan
Hardware
  Layout Design QA
  Final review of layout
  CAM activity
  Gerber (DFM, DFA) data generation & review
  Proto PCB Fabrication
  Component Ordering
EVSE Testing
  Complete test cases for 2 new EVSE features
  Complete test cases for 2 new OCPP functionalities

## Slide 7: Key Decisions (No Change)
Python 2.7.6 will be used
(https://www.python.org/download/releases/2.7.6/)
APC8958 (version 6) IP power switch will be used (http://www.apc.com/shop/us/en/products/Rack-PDU-2G-Switched-ZeroU-20A-208V-16A-230V-7-C13-1-C19/P-AP8958)
OCPP Open Source Server
(https://github.com/ChargeTimeEU/Java-OCA-OCPP)
Siemens proprietary configuration parameters for OCPP (out of scope)
  EnableOfflineCharging
  AuthorizationRequired
  NonAuthorizedTag
  EVSideDisconnectDuration
From previous week’s WSR:
eInfochips will be reshuffling some of the priorities to resolve Sesha’s direct dependencies first before she goes on vacation
The expected behaviour of the test cases may be tweaked later based on the actual output we see after we have the EVSE units in hand

## Slide 8: Dependencies and help needed
  Shipping EVSE units – Amit
    Delay in this will impact schedule
  Waiting on feedback for OCPP questions – Paul
  Address QTS queries - Sesha
  Review feedback for the test cases completed – Sesha/Paul
  Need access to commissioning web pages for automation

## Slide 9: Miscellaneous Information/Updates
  Wi-Fi module received at eInfochips (Ahmedabad)
  4 STE Eval boards for car simulator received at eInfochips Ahmedabad
  4 50 Amp Current Transformer received at eInfochips Ahmedabad

## Slide 10
Thank you
India Headquarters 11/A-B, Chandra Colony, Off C.G. Road, Ellisbridge, Ahmedabad 380 006 Tel: +91-79-2656 3705 Fax: +91-79-2656 0722
US Headquarters 1230 Midas Way, Suite# 200, Sunnyvale, CA 94085. Tel:+1-408-496-1882 Fax: +1-801-650-1480
Pune : 91-20-41402525
Chennai : 91-44-42121594
Austin : 1-512-519-9164
Boston : 1-508-870-0500
Chicago : 1- 847 387 7225
Dallas : 1-214 641-9293
Germany : 49-160-741-8940
Japan : 81-3-5789-5854
Notes: 81-3-5789-5854
44 - 42121594