## Slide 1: Siemens EVSE Automation Weekly Project Status Updates
Date: 30th November 2017
eInfochips Confidential
Product Design Services & Solutions
Product Engineering| Semiconductor

## Slide 2: Agenda
  Work status this week: 23rd November to 29th November
  Plan for next week: 30th November to 6th December
  Key Decisions
  Dependencies and help needed
  Miscellaneous Information/Updates

## Slide 3: Work Status for this week
Test Automation Framework
  Automation framework design and architecture - Done
  Building Python project using Maven to create POM file and configure it in framework - Done
  OCPP Server and interface development – In Progress
    Get configuration, change configuration and clear charging profile request and confirmation
  Preparing request response classes according to JSON format that are being sent and received by EVSE and server
  Test Plan - Progress
Hardware
  Layout Design QA
  Final review of layout
  Component Ordering
EVSE Testing
  Completed test cases for 4 new OCPP functionalities (listed on slide # 5); Completed all test cases for OCPP functionalities

## Slide 4: Work Status – EVSE Features Test Cases (No Change)
# | Features | Test Cases Status
1 | System Configuration | Done
2 | SAE J1772 State levels | Done
3 | CCID Time Response (I vs. non-I) | Not started
4 | CCID Auto Reset (15min.) | In Progress
5 | Max Current Switch Settings | Done
6 | Pause Button (Local & Web App) | In Progress
7 | 2/4/6/8 Hr. Delay Button | Not started
8 | Cold Start with Random Delay | In Progress
9 | Over/ Under Voltage detection | Done
10 | Function Memory after Power Cycle (Pause, Delay, Remote, Lock) | In Progress
11 | Local Lock with Lock Enabled | In Progress
12 | Local Lock with Lock Disabled | In Progress
13 | Serial Communications (RS-485) | Done
14 | Fault test & Non Volatile Memory (Fault Log) | In Progress
15 | Non Volatile Memory (Energy Measurements) | Done
16 | RTC | Done
17 | Remote Control Via Web App | No separate test for this
18 | OTA updateable (CC2538) | Not started
19 | Remote Control via OCPP App | Refer separate table for OCPP
20 | EVSE Commissioning | Done
21 | Power Level adjustment (Verify pilot duty cycle) | Done
22 | Local Override of Cloud Remote | In Progress
23 | Firmware version verification on the Web App | In Progress

## Slide 5: Work Status – OCPP Features Test Cases
# | Feature | Test Cases Status
1 | BootNotification | Done
2 | Heartbeat | Done
3 | MeterValues | Done
4 | StartTransaction | Done
5 | StatusNotification | Done
6 | StopTransaction | Done
7 | ChangeConfiguration | Done
8 | ClearChargingProfile | Done
9 | GetConfiguration | Done
10 | RemoteStartTransaction | Done
11 | RemoteStopTransaction | Done
12 | SetChargingProfileRequest | Done
13 | TriggerMessageRequest | Done

## Slide 6: Work plan for next week
Test Automation Framework
  Implementation of Webpages in Pytest Automation framework for Cloud Web app
  Verification of Socket connection and communication with OCPP Server
  Jenkins support for Trigger a build after every SVN commit and build failure notification via Email
  Modbus communication between test automation framework and car simulator
  OCPP Server
    Handling of remote start and stop transaction request and confirmation
    Preparing request response classes according to JSON format that are being sent and received by device and server
  Test Plan
Hardware
  Review comment implementation from Siemens
  CAM activity
  Gerber (DFM, DFA) data generation & review
  Proto PCB Fabrication
  Component shipment to eInfochips
EVSE Testing
  Complete test cases for 2 new EVSE features

## Slide 7: Key Decisions
No New updates

## Slide 8: Dependencies and help needed
  Shipping EVSE units – Amit
    Schedule impact
  Address QTS queries (13 items open) - Paul
  Review feedback for the OCPP test cases completed – Paul
  Review the EVSE Car Simulator H/W schematic & layout files – Paul
  Access to commissioning web pages for automation

## Slide 9: Miscellaneous Information/Updates
List of team members shared with Amit

## Slide 10
Thank you
India Headquarters 11/A-B, Chandra Colony, Off C.G. Road, Ellisbridge, Ahmedabad 380 006 Tel: +91-79-2656 3705 Fax: +91-79-2656 0722
US Headquarters 1230 Midas Way, Suite# 200, Sunnyvale, CA 94085. Tel:+1-408-496-1882 Fax: +1-801-650-1480
Pune : 91-20-41402525
Chennai : 91-44-42121594
Austin : 1-512-519-9164
Boston : 1-508-870-0500
Chicago : 1- 847 387 7225
Dallas : 1-214 641-9293
Germany : 49-160-741-8940
Japan : 81-3-5789-5854
Notes: 81-3-5789-5854
44 - 42121594