## Slide 1: Siemens EVSE Automation Weekly Project Status Updates
Date: 7th December 2017
eInfochips Confidential
Product Design Services & Solutions
Product Engineering| Semiconductor

## Slide 2: Agenda
  Work status this week: 30th November to 6th December
  Plan for next week: 7th December to 13th December
  Key Decisions
  Dependencies and help needed
  Miscellaneous Information/Updates

## Slide 3: Work Status for this week
Test Automation Framework
  Implementation of Webpages in Pytest Automation framework for Cloud Web app – In Progress
  Verification of Socket connection and communication with OCPP Server – In Progress
  Jenkins support for Trigger a build after every SVN commit and build failure notification via Email – Completed
  Modbus communication between test automation framework and car simulator – In Progress
  OCPP Server
    Handling of trigger message, boot notification and heartbeat request and confirmation
    Preparing request response classes according to JSON format that are being sent and received by device and server - Done
  Test Plan – In Progress
Hardware
  CAM activity
  Gerber (DFM, DFA) data generation & review
  Proto PCB Fabrication (In Progress)
  Component received at eInfochips and shipped to Assembly house
  Assembly Instruction document preparation
  Stencil Fabrication (In Progress)
EVSE Testing
  Completed test cases for 1 new EVSE functionality (listed on slide # 4)

## Slide 4: Work Status – EVSE Features Test Cases
# | Features | Test Cases Status
1 | System Configuration | Done
2 | SAE J1772 State levels | Done
3 | CCID Time Response (I vs. non-I) | Not started
4 | CCID Auto Reset (15min.) | In Progress
5 | Max Current Switch Settings | Done
6 | Pause Button (Local & Web App) | In Progress
7 | 2/4/6/8 Hr. Delay Button | Not started
8 | Cold Start with Random Delay | In Progress
9 | Over/ Under Voltage detection | Done
10 | Function Memory after Power Cycle (Pause, Delay, Remote, Lock) | In Progress
11 | Local Lock with Lock Enabled | In Progress
12 | Local Lock with Lock Disabled | In Progress
13 | Serial Communications (RS-485) | Done
14 | Fault test & Non Volatile Memory (Fault Log) | In Progress
15 | Non Volatile Memory (Energy Measurements) | Done
16 | RTC | Done
17 | Remote Control Via Web App | No separate test for this
18 | OTA updateable (CC2538) | Done
19 | Remote Control via OCPP App | Refer separate table for OCPP
20 | EVSE Commissioning | Done
21 | Power Level adjustment (Verify pilot duty cycle) | Done
22 | Local Override of Cloud Remote | In Progress
23 | Firmware version verification on the Web App | In Progress

## Slide 5: Work Status – OCPP Features Test Cases (No Change)
# | Feature | Test Cases Status
1 | BootNotification | Done
2 | Heartbeat | Done
3 | MeterValues | Done
4 | StartTransaction | Done
5 | StatusNotification | Done
6 | StopTransaction | Done
7 | ChangeConfiguration | Done
8 | ClearChargingProfile | Done
9 | GetConfiguration | Done
10 | RemoteStartTransaction | Done
11 | RemoteStopTransaction | Done
12 | SetChargingProfileRequest | Done
13 | TriggerMessageRequest | Done

## Slide 6: Work plan for next week
Test Automation Framework
  Create and verify sample test for pytest automation framework
  Code implementation of commissioning page for Cloud Web app
  Execution of Single/Multiple/All Tests from Jenkins
  Modbus communication between test automation framework and car simulator
  OCPP Server
    Handling of remote start and stop transaction request and confirmation
  Test Plan
Hardware
  Proto PCB Fabrication Completion
  Stencil Fabrication Completion
  Start of PCB Assembly
EVSE Testing
  Complete test cases for 1 new EVSE feature

## Slide 7: Key Decisions
No New updates

## Slide 8: Dependencies and help needed
  Address QTS queries (9 items open) – Paul/Amit
  Share all the required test accessories for Car Simulator HW or their part numbers
    For e.g. Step down Transformer, Load resistor, Current Transformer for Scaled down load current
  Share Complete Connection diagram with pin number and connector details around Car Simulator board and EVSE
  Review feedback for the OCPP test cases completed – Paul
  Shipping EVSE units – Amit
    Schedule impact
  Review the EVSE Car Simulator H/W schematic & layout files – Paul
  Access to commissioning web pages for automation

## Slide 9: Miscellaneous Information/Updates
Siemens signoff on schematic and layout received
Reduced the frequency of query discussion call
4 VersiChargeSG units in transit (ETA middle of next week)
Updated schedule shared with Siemens – Delay of 3 weeks anticipated

## Slide 10
Thank you
India Headquarters 11/A-B, Chandra Colony, Off C.G. Road, Ellisbridge, Ahmedabad 380 006 Tel: +91-79-2656 3705 Fax: +91-79-2656 0722
US Headquarters 1230 Midas Way, Suite# 200, Sunnyvale, CA 94085. Tel:+1-408-496-1882 Fax: +1-801-650-1480
Pune : 91-20-41402525
Chennai : 91-44-42121594
Austin : 1-512-519-9164
Boston : 1-508-870-0500
Chicago : 1- 847 387 7225
Dallas : 1-214 641-9293
Germany : 49-160-741-8940
Japan : 81-3-5789-5854
Notes: 81-3-5789-5854
44 - 42121594