## Slide 1: Siemens EVSE Automation Weekly Project Status Updates
Date: 18th January 2018
eInfochips Confidential
Product Design Services & Solutions
Product Engineering| Semiconductor

## Slide 2: Agenda
  Work status this week: 11th January to 17th January
  Plan for next week: 18th January to 24th January
  Key Decisions
  Dependencies and help needed
  Miscellaneous Information/Updates

## Slide 3: Work status for this week
Test Automation Framework
  MSP430 and CC2538 logs parsing - Completed
  Pause / Delay Web Automation - Completed
  Test plan & test setup documentation – Completed
  Release v1.0 shared with Siemens
Hardware
  Dependency on open queries
EVSE Testing
  Continue with test script/procedure creation on python

## Slide 4: Work Status – EVSE Features Test Cases (No Change)
# | Features | Test Cases Status
1 | System Configuration | Done
2 | SAE J1772 State levels | Done
3 | CCID Time Response (I vs. non-I) | Done
4 | CCID Auto Reset (15min.) | Done
5 | Max Current Switch Settings | Done
6 | Pause Button (Local & Web App) | Done
7 | 2/4/6/8 Hr. Delay Button | Done
8 | Cold Start with Random Delay | Done
9 | Over/ Under Voltage detection | Done
10 | Function Memory after Power Cycle (Pause, Delay, Remote, Lock) | Done
11 | Local Lock with Lock Enabled | Done
12 | Local Lock with Lock Disabled | Done
13 | Serial Communications (RS-485) | Done
14 | Fault test & Non Volatile Memory (Fault Log) | Done
15 | Non Volatile Memory (Energy Measurements) | Done
16 | RTC | Done
17 | Remote Control Via Web App | No separate test for this
18 | OTA updateable (CC2538) | Done
19 | Remote Control via OCPP App | Done
20 | EVSE Commissioning | Done
21 | Power Level adjustment (Verify pilot duty cycle) | Done
22 | Local Override of Cloud Remote | Done
23 | Firmware version verification on the Web App | Done

## Slide 5: Work plan for next week
Test Automation Framework
  Test plan & test setup documentation – update based on testing progress
  Commissioning of utility version of VersiChargeSG
  Connect car simulator with EVSE
EVSE Testing
  Continue with test script/procedure creation on python
Hardware
  Dependency on open queries

## Slide 6: Key Decisions (No Change)
No New updates

## Slide 7: Dependencies and help needed
  Review feedback for the EVSE and OCPP test cases completed
  Address QTS queries (13 items open) – on hold
  Share all the required test accessories for Car Simulator HW or their part numbers – on hold
    For e.g. Step down Transformer, Load resistor, Current Transformer for Scaled down load current
  Share Complete Connection diagram with pin number and connector details around Car Simulator board and EVSE – on hold

## Slide 8: Miscellaneous Information/Updates
26th January Holiday at eInfochips India office

## Slide 9
Thank you
India Headquarters 11/A-B, Chandra Colony, Off C.G. Road, Ellisbridge, Ahmedabad 380 006 Tel: +91-79-2656 3705 Fax: +91-79-2656 0722
US Headquarters 1230 Midas Way, Suite# 200, Sunnyvale, CA 94085. Tel:+1-408-496-1882 Fax: +1-801-650-1480
Pune : 91-20-41402525
Chennai : 91-44-42121594
Austin : 1-512-519-9164
Boston : 1-508-870-0500
Chicago : 1- 847 387 7225
Dallas : 1-214 641-9293
Germany : 49-160-741-8940
Japan : 81-3-5789-5854
Notes: 81-3-5789-5854
44 - 42121594