## Slide 1: Siemens EVSE Automation Weekly Project Status Updates
Date: 9th November 2017
eInfochips Confidential
Product Design Services & Solutions
Product Engineering| Semiconductor

## Slide 2: Agenda
  Work status this week: 3rd November to 9th November
  Plan for next week: 10th November to 16th November
  Key Decisions
  Dependencies and help needed
  Miscellaneous Information/Updates

## Slide 3: Work Status for this week
  EVSE features test cases & scenarios
    System Configuration (100%)
    SAE J1772 State levels (100%)
    Max. current level adjustments (100%)
    Non volatile memory (energy measurements) (100%)
    Over & under voltage faults (75%)
    RTC (75%)
    Serial communication (50%)
  OCPP test cases & scenarios (draft)
    Get Configuration
    Change Configuration
    Trigger Message
  Hardware
    Schematic symbol review
    Schematic update complete
    BOM QA

## Slide 4: Work Plan for next week
  EVSE features & test scenarios
    Over & under voltage faults
    Serial communication
    RTC
    Pause
    Commissioning
  OCPP test cases & scenarios
    Update the OCPP tests based on Paul’s feedback
    Heartbeat
    MeterValues
  Hardware
    Footprint review
    New part footprint creation
    Placement & routing of the new parts added
  Share project schedule/timeline with Siemens

## Slide 5: Key Decisions
eInfochips will be reshuffling some of the priorities to resolve Sesha’s direct dependencies first before she goes on vacation
The expected behaviour of the test cases may be tweaked later based on the actual output we see after we have the EVSE units in hand

## Slide 6: Dependencies and help needed
  Shipping EVSE units - Amit
  Need details of custom configuration parameters for OCPP – Paul
  Address QTS queries (8 open questions) - Sesha
  Review feedback for the test cases completed – Sesha/Paul

## Slide 7: Miscellaneous Information/Updates
  Wi-Fi module received at eInfochips (Cincinnati)
  4 STE Eval boards for car simulator in transit (ETA next week)

## Slide 8
Thank you
India Headquarters 11/A-B, Chandra Colony, Off C.G. Road, Ellisbridge, Ahmedabad 380 006 Tel: +91-79-2656 3705 Fax: +91-79-2656 0722
US Headquarters 1230 Midas Way, Suite# 200, Sunnyvale, CA 94085. Tel:+1-408-496-1882 Fax: +1-801-650-1480
Pune : 91-20-41402525
Chennai : 91-44-42121594
Austin : 1-512-519-9164
Boston : 1-508-870-0500
Chicago : 1- 847 387 7225
Dallas : 1-214 641-9293
Germany : 49-160-741-8940
Japan : 81-3-5789-5854
Notes: 81-3-5789-5854
44 - 42121594