## Slide 1: Siemens EVSE Automation Weekly Project Status Updates
Date: 21st December 2017
eInfochips Confidential
Product Design Services & Solutions
Product Engineering| Semiconductor

## Slide 2: Agenda
  Work status this week: 14th December to 20th December
  Plan for next week: 21st December to 27th December
  Key Decisions
  Dependencies and help needed
  Miscellaneous Information/Updates

## Slide 3: Work status for next week
Test Automation Framework
  Code implementation of commissioning page for Cloud Web app - Done
  OCPP Server internal review in progress
  Autonomous mode test code via car simulator software
    May need to split autonomous mode and manual mode owing to memory limitations
  Test Plan
Hardware
  Baking of Bare PCBs and components for Assembly (completed)
  PCB Assembly (Completed)
  Board shipped to eInfochips

## Slide 4: Work Status – EVSE Features Test Cases (No Change)
# | Features | Test Cases Status
1 | System Configuration | Done
2 | SAE J1772 State levels | Done
3 | CCID Time Response (I vs. non-I) | In Progress
4 | CCID Auto Reset (15min.) | In Progress
5 | Max Current Switch Settings | Done
6 | Pause Button (Local & Web App) | In Progress
7 | 2/4/6/8 Hr. Delay Button | Not started
8 | Cold Start with Random Delay | In Progress
9 | Over/ Under Voltage detection | Done
10 | Function Memory after Power Cycle (Pause, Delay, Remote, Lock) | In Progress
11 | Local Lock with Lock Enabled | In Progress
12 | Local Lock with Lock Disabled | In Progress
13 | Serial Communications (RS-485) | Done
14 | Fault test & Non Volatile Memory (Fault Log) | In Progress
15 | Non Volatile Memory (Energy Measurements) | Done
16 | RTC | Done
17 | Remote Control Via Web App | No separate test for this
18 | OTA updateable (CC2538) | Done
19 | Remote Control via OCPP App | Done
20 | EVSE Commissioning | Done
21 | Power Level adjustment (Verify pilot duty cycle) | Done
22 | Local Override of Cloud Remote | Done
23 | Firmware version verification on the Web App | Done

## Slide 5: Work plan for next week
Test Automation Framework
  Execution of test case steps based on depth(priority) value passed from Jenkins
  Test report and logging
  Communication from framework to EVSE
  Autonomous mode test code via car simulator software
  OCPP Server completion
  Test Plan
Hardware
  Visual verification of Assembly
  DC Power rails Impedance measurement
  DC Power supply testing of the Car simulator board
EVSE Testing
  Start test scripts from test cases completed

## Slide 6: Key Decisions (No Change)
No New updates

## Slide 7: Dependencies and help needed
  Address QTS queries (9 items open) – on hold
  Share all the required test accessories for Car Simulator HW or their part numbers – on hold
    For e.g. Step down Transformer, Load resistor, Current Transformer for Scaled down load current
  Share Complete Connection diagram with pin number and connector details around Car Simulator board and EVSE – on hold
  Review feedback for the OCPP test cases completed – Paul
  Number of power supply/accessories for car simulator - Amit

## Slide 8: Miscellaneous Information/Updates
4 VersiChargeSG units in transit (received at Ahmedabad)
25th December 2017 – Christmas holiday at eInfochips

## Slide 9
Thank you
India Headquarters 11/A-B, Chandra Colony, Off C.G. Road, Ellisbridge, Ahmedabad 380 006 Tel: +91-79-2656 3705 Fax: +91-79-2656 0722
US Headquarters 1230 Midas Way, Suite# 200, Sunnyvale, CA 94085. Tel:+1-408-496-1882 Fax: +1-801-650-1480
Pune : 91-20-41402525
Chennai : 91-44-42121594
Austin : 1-512-519-9164
Boston : 1-508-870-0500
Chicago : 1- 847 387 7225
Dallas : 1-214 641-9293
Germany : 49-160-741-8940
Japan : 81-3-5789-5854
Notes: 81-3-5789-5854
44 - 42121594