## Slide 1: Siemens EVSE Automation Weekly Project Status Updates
Date: 28th December 2017
eInfochips Confidential
Product Design Services & Solutions
Product Engineering| Semiconductor

## Slide 2: Agenda
  Work status this week: 21st December to 27th December
  Plan for next week: 28th December to 3rd January
  Key Decisions
  Dependencies and help needed
  Miscellaneous Information/Updates

## Slide 3: Work status for this week
Test Automation Framework
  Execution of test case steps based on depth(priority) value passed from Jenkins - Done
  Test report and logging - Done
  Communication from framework to EVSE – In Progress
  Autonomous mode test code via car simulator software – 1 test done
  OCPP Server completion – Internal review in progress
  Test plan & test setup documentation – In Progress
Hardware
  Visual verification of Assembly (Completed on one board)
  DC Power rails Impedance measurement (Completed on one board)
  DC Power supply testing of the Car simulator board (Completed on one board)
EVSE Testing
  Started test scripts – 1 test script completed

## Slide 4: Work Status – EVSE Features Test Cases (No Change)
# | Features | Test Cases Status
1 | System Configuration | Done
2 | SAE J1772 State levels | Done
3 | CCID Time Response (I vs. non-I) | In Progress
4 | CCID Auto Reset (15min.) | In Progress
5 | Max Current Switch Settings | Done
6 | Pause Button (Local & Web App) | In Progress
7 | 2/4/6/8 Hr. Delay Button | Not started
8 | Cold Start with Random Delay | In Progress
9 | Over/ Under Voltage detection | Done
10 | Function Memory after Power Cycle (Pause, Delay, Remote, Lock) | In Progress
11 | Local Lock with Lock Enabled | In Progress
12 | Local Lock with Lock Disabled | In Progress
13 | Serial Communications (RS-485) | Done
14 | Fault test & Non Volatile Memory (Fault Log) | In Progress
15 | Non Volatile Memory (Energy Measurements) | Done
16 | RTC | Done
17 | Remote Control Via Web App | No separate test for this
18 | OTA updateable (CC2538) | Done
19 | Remote Control via OCPP App | Done
20 | EVSE Commissioning | Done
21 | Power Level adjustment (Verify pilot duty cycle) | Done
22 | Local Override of Cloud Remote | Done
23 | Firmware version verification on the Web App | Done

## Slide 5: Work plan for next week
Test Automation Framework
  Communication from framework to EVSE
  Test builds via Jenkins
  OCPP Server release
  Test plan & test setup documentation – In Progress
Hardware
  Testing of the RL2 to RL5 ckt which changes the resistance on Pilot signal
  Testing of Diode fault relay (SSR11 ) ckt
  Testing of the U6 & nearby ckt which measures duty cycle & voltage level of pilot signal
EVSE Testing
  Continue with test script/procedure creation on python

## Slide 6: Key Decisions (No Change)
No New updates

## Slide 7: Dependencies and help needed
  Address QTS queries (9 items open) – on hold
  Share all the required test accessories for Car Simulator HW or their part numbers – on hold
    For e.g. Step down Transformer, Load resistor, Current Transformer for Scaled down load current
  Share Complete Connection diagram with pin number and connector details around Car Simulator board and EVSE – on hold
  Review feedback for the OCPP test cases completed – Paul
  Number of power supply/accessories for car simulator - Amit

## Slide 8: Miscellaneous Information/Updates
Car Simulator Hardware received at eInfochips Ahmedabad office
NEMA 6-50R 50A 250V receptacle for EVSE ordered – In Transit

## Slide 9
Thank you
India Headquarters 11/A-B, Chandra Colony, Off C.G. Road, Ellisbridge, Ahmedabad 380 006 Tel: +91-79-2656 3705 Fax: +91-79-2656 0722
US Headquarters 1230 Midas Way, Suite# 200, Sunnyvale, CA 94085. Tel:+1-408-496-1882 Fax: +1-801-650-1480
Pune : 91-20-41402525
Chennai : 91-44-42121594
Austin : 1-512-519-9164
Boston : 1-508-870-0500
Chicago : 1- 847 387 7225
Dallas : 1-214 641-9293
Germany : 49-160-741-8940
Japan : 81-3-5789-5854
Notes: 81-3-5789-5854
44 - 42121594